## Sheet1
Defect Id | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | screenshot
df_id_001 | A warning message 'Create button is not working even after giving all the information correctly'. | 1. Click on 'Sign up' option 2. Enter new Account Details into the Fields (Full Name,Email address ,Password,Confirm Password) 3. Click on 'Create Account' button | User should be logged in successfully and taken to Home page . | User do not log in successfully and do not taken to Home page . | high | high | defect vedio
df_id_002 | A valid email address typically follows the pattern "username@example.com." In this case, "111@gmail.com" seems to be missing the username part. | 1. Click on 'Sign up' option 2. Click the 'Email feild and put it in wrong email 3. Click on 'Create Account' button | A valid email address typically follows the pattern "username@example.com." In this case, "111@gmail.com" seems to be missing the username part. | In this case, "111@gmail.com" seems to be missing the username part is not displaying and taken to home page. | major | high | defect vedio
df_id_003 | A warning message 'invalid Email Address ' and invalid full name is not displayed and logged in and taken to the home page. | 1. Click on 'Sign up' option 2. Enter new Account Details into the Fields invalid Full Name,Password ,Confirm Password and invalid email ) 3.Click on 'Create Account' button | A warning message 'invalid Email Address ' and invalid full name should be displayed | A warning message 'invalid Email Address ' and invalid full name is not displayed and logged in and taken to the home page. | major | high
df_id_004 | User should not be logged in successfully and a warning message ' invalid full name should be displayed | 1. Click on 'Sign up' option 2. Enter new Account Details into the Fields invalid Full Name , invalid email but do not fill password and confirm password ) 3.Click on 'Create Account' button | User should not be logged in successfully and a warning message ' invalid full name should be displayed | a warning message ' invalid full name should be displayed " is not displayed.' | major | high
df_id_005 | A warning message 'invalid full name,invalid Email Address should be displayed | 1. Click on 'Sign up' option 2. Enter new Account Details into the Fields invalid Full Name , invalid email ,valid password and confirm password ) 3.Click on 'Create Account' button | A warning message 'invalid full name,invalid Email Address should be displayed | A warning message 'invalid full name,invalid Email Address is not displayed' | major | high
df_id_006 | A warning message - 'full name is invalid , should be displayed | 1. Click on 'Sign up' option 2. Enter new Account Details into the Fields invalid Full Name ,valid email ,valid password and confirm password ) 3.Click on 'Create Account' button | A warning message - 'full name is invalid , should be displayed | A warning message - 'full name is invalid , should be displayed "is not displayed | major | low
df_id_007 | A warning message "The password and confirm password does not match should be displayed under the password and confirm password feild | 1. Click on 'Sign up' option 2.Don't enter anything into the Fields (Full Name,Email address ) 3.Enter different password into password and confirm password feild 4. Click on 'Create Account' button | A warning message "The password and confirm password does not match should be displayed under the password and confirm password feild | A warning message "The password and confirm password does not match should be displayed under the password and confirm password feild" do not displayed. | major | high
df_id_008 | After logging in with correct information,if you log in again with that information,it cannot work. | 1. Click on 'Sign up' option 2. Enter new Account Details into the Fields (Full Name,Email address ,Password,Confirm Password) 3. Click on 'Create Account' button | User should be logged in successfully and taken to Home page . | User do not log in successfully and do not taken to Home page . | high | high